## Sheet1
Phase | Sprint | Story # | User Stories | Task | Business Priority | Story Points | Hours Effort | Responsible
As a Wikiviz user I want an application that…
Research and Design | Sprint 0
1/13 - 1/24 |  |  |  | Research available libraries, algorithms, prior projects |  |  | 15 | ALL
|  |  |  | Write SRS |  |  | 15 | AR,SM
|  |  |  | SUM |  |  | 30
Development/Research and Design- Iteration 1 | Sprint 1 | 1 | allows me to search Wikipedia |  | 1 | 2
1/27 - 2/7 |  |  |  | Set up initial dev environment |  |  | 3 | ALL
|  |  |  | Create window with search box |  |  | 2 | ER
|  |  |  | Send user query to Wikipedia |  |  | 2 | AR
|  |  |  | Parse returned content for image, text, links |  |  | 2 | SM
|  | 2 | shows search results from Wikipedia in a visual way |  | 1 | 3
|  |  |  | Display search result (image, title) on screen |  |  | 2 | ER
|  |  |  | On click, show full text on screen, then remove text when clicked again |  |  | 2 | ER
|  |  |  | Add link to full Wikipedia page |  |  | 1 | ER
|  | 3 | shows other content related to my search in a way that shows the relationships between concepts |  | 1 | 3
|  |  |  | Store data in graph structure |  |  | 2 | ALL
|  |  |  | Draw graph on screen |  |  | 6 | ER
|  | 4 | autosuggests search terms |  | 3 | 3
|  |  |  | Send each keypress to Wikipedia, return autosuggested terms (or find way to run query locally) |  |  | 6 | AR
|  |  |  | Display autosuggested terms in box |  |  | 3 | ER
Related Research and Design
|  |  |  | Kivy demo (GUI) |  |  | 2 | ER
|  |  |  | BeautifulSoup demo (text parser) |  |  | 2 | SM
|  |  |  | Biocortex demo (Wikipedia scraping method) |  |  | 2 | AR
|  |  |  | Research networking |  |  | 2 | AR
|  |  |  | SUM |  | 11 | 29
Development/Research and Design- Iteration 2 | Sprint 2
2/10 - 2/21 |  | Related Research and Design
|  |  |  | Use case diagram |  |  | 2 | ER
|  |  |  | Class diagrams |  |  | 5 | ALL
|  |  |  | Sequence diagram |  |  | 2 | AR
|  |  |  | Review Doxygen (documentation method) |  |  | 2 | ALL
|  | 2 | shows search results from Wikipedia in a visual way |  | 1 | 2
|  |  |  | Fit images to nodes (masking) |  |  | 2 | ER
|  | 1 | allows me to search Wikipedia |  | 1 | 1
|  |  |  | Set network throttle limits |  |  | 1 | AR
|  | 4 | create Mac version of app (ongoing) |  | 3 | 6
|  |  |  | Adapt UI to be Mac-compatible |  |  | 8 | AR
|  |  |  | SUM |  | 9 | 24
Development - Iteration 3 | Sprint 3
2/24 - 3/7 |  | 1 | allows me to search Wikipedia |  | 1 | 2
|  |  |  | Add button to clear search and start over |  |  | 2 | ER
|  | 3 | shows other content related to my search in a way that shows the relationships between concepts |  | 1 | 3
|  |  |  | Parse search result for links, determine most related |  |  | 2 | SM
|  | 5 | allow me to adjust the amount of information I’m viewing |  | 2 | 3
|  |  |  | Create option slider |  |  | 3 | ER
|  |  |  | Adjust number of nodes shown according to slider |  |  | 2 | ER
|  | 6 | is fast and responsive |  | 2 | 5
|  |  |  | Improve networking performance (threads) |  |  | 4 | AR
|  |  |  | Preload media assets |  |  | 4 | AR
|  | 7 | shows a summary of Wikipedia content |  | 3 | 3
|  |  |  | Implement text summarization algorithm |  |  | 12 | SM
|  |  |  | SUM |  | 21 | 29
Development - Iteration 5: Stretch Goals | Sprint 4
3/10-3/21 |  | 9 | is dynamic and fun to explore, with animations and a unique interface |  | 3 | 3
|  |  |  | Add ability to drag and reposition nodes |  |  | 3 | ER
|  |  |  | Add panning and zoom controls |  |  | 3 | ER
|  | 8 | allows me to share what I find with others |  | 2 | 5
|  |  |  | Export image of graph, allow user to save |  |  | 6 | AR
|  |  |  | Send user to social networking site with link and preview image |  |  | 6 | AR
|  | 10 | allows me to explore many nodes, generating a large viewing graph |  | 4 | 2
|  |  |  | Improve graph drawing performance |  |  | 4 | ER
|  |  |  | SUM |  | 10 | 22
Development/Testing | Sprint 5
3/24 - 4/4 |  | 11 | shows content from Google, not just Wikipedia |  | 5 | 8
|  |  |  | Adapt networking to also use Google as a source |  |  | 4 | AR
|  |  |  | Adapt parsing to be flexible enough for Google |  |  | 12 | SM
|  |  |  | Add UI Controls to switch between Google and Wiki |  |  | 6 | ER
|  |  | Component and Integration testing |  |  |  | 15 | ALL
|  |  |  | SUM |  |  | 37
Testing, Buffer | Sprint 5
4/7 - 4/17 |  |  | End-to-end testing |  |  |  | 15 | ALL
|  |  |  | SUM |  |  | 15
TOTALS | TOTALS |  |  |  |  | 49 | 184